## Pert Chart
Requirement
Gathering
7 Days
Menentukan kebutuhan pengguna (admin, guru, siswa).
001
24 Jan 2025
30 Jan 2025
7 Days
Membuat daftar fitur yang akan diimplementasikan.
002
31 Jan 2025
06 Feb 2025
Design
21 Days
Mendesain antarmuka pengguna (UI/UX).
003
07 Feb 2025
27 Feb 2025
21 Days
Mendesain database dan diagram kelas.
004
07 Feb 2025
27 Feb 2025
Development
7 Days
Mengembangkan modul manajemen pengguna.
005
28 Feb 2025
06 Mar 2025
6 Days
Mengembangkan modul kelas dan materi.
006
07 Mar 2025
12 Mar 2025
8 Days
Mengembangkan modul ujian dan evaluasi.
007
13 Mar 2025
20 Mar 2025
8 Days
Integrasi Frontend, Backend, dan Database.
008
21 Mar 2025
27 Mar 2025
Testing
5 Days
Pengujian fungsionalitas tiap modul.
009
28 Mar 2025
01 April 2025
9 Days
Pengujian Integrasi Sistem.
010
02 April 2025
10 April 2025
Deployment
5 Days
Deploy sistem ke server.
011
11 Apr 2025
15 Apr 2025
16 Days
Memberikan pelatihan kepada pengguna awal (user training).
012
16 Apr 2025
1 May 2025

## Gantt Chart
Summary | [5 empty] | Project Date: |  |  | 2025-01-24
Project Start: 24/01/2025 |  | Total Effective Duration: 98 Days |  | Project End: 01-May-25
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20
Don't Change | Fill This | time axis 2025-01-24 to 2025-06-12
ID | Phase ID | Task ID | Name | Start Date | End Date | time axis 2025-01-24 to 2025-06-12
1.0 | 1 | 0 | Requirement Gathering | 2025-01-24 | 2025-02-06
1.1 | 1 | 1 | Menentukan kebutuhan pengguna (admin, guru, siswa). | 2025-01-24 | 2025-01-30
1.2 | 1 | 2 | Membuat daftar fitur yang akan diimplementasikan. | 2025-01-31 | 2025-02-06
2.0 | 2 | 0 | Design | 2025-02-07 | 2025-02-27
2.1 | 2 | 1 | Mendesain antarmuka pengguna (UI/UX). | 2025-02-07 | 2025-02-27
2.2 | 2 | 2 | Mendesain database dan diagram kelas. | 2025-02-07 | 2025-02-27
3.0 | 3 | 0 | Development | 2025-02-28 | 2025-03-27
3.1 | 3 | 1 | Mengembangkan modul manajemen pengguna. | 2025-02-28 | 2025-03-06
3.2 | 3 | 2 | Mengembangkan modul kelas dan materi. | 2025-03-07 | 2025-03-12
3.3 | 3 | 3 | Mengembangkan modul ujian dan evaluasi. | 2025-03-13 | 2025-03-20
3.4 | 3 | 4 | Integrasi Frontend, Backend, dan Database. | 2025-03-21 | 2025-03-27
4.0 | 4 | 0 | Testing | 2025-03-28 | 2025-04-10
4.1 | 4 | 1 | Pengujian fungsionalitas tiap modul. | 2025-03-28 | 2025-04-01
4.2 | 4 | 2 | Pengujian integrasi sistem. | 2025-04-02 | 2025-04-10
5.0 | 5 | 0 | Deployment | 2025-04-11 | 2025-05-01
5.1 | 5 | 1 | Deploy sistem ke server. | 2025-04-11 | 2025-04-15
5.2 | 5 | 2 | Memberikan pelatihan kepada pengguna awal (user training). | 2025-04-16 | 2025-05-01
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.